Sample VISTA Assignment Description (VAD)

Cody Rouge Community Action Alliance – Rouge Park Plan and Neighborhood Health Connections

Sponsoring Organization: -DOI + Cody Rouge Community Action Alliance Project Name: DOI/VISTA Project Number: -leave blank- Project Period: -leave blank-

Site Name (if applicable): Cody Rouge Neighborhood – Detroit, MI

Focus Area(s) Primary: Healthy Futures – Economic Opportunities Secondary: Environmental Stewardship

Note: If your VAD is not accepted, the State Office will note the reason(s) why here.

VISTA Assignment Objectives and Member Activities

Goal of the Project: In collaboration with the NPS RTCA the DOI/VISTA will perform two primary functions to bring community members in the Rouge Park Neighborhoods out of poverty. 1) Increase community health through the development of partnerships with local health organizations to promote nutritional education and disease prevention programs at the park and 2) work to develop a Youth Conservation Corps to impact long-term park infrastructure improvements while benefiting participants by increasing employment skills.

Objective of the Assignment DOI/VISTA will coordinate with local health organizations to provide outreach, training, service learning opportunities, and nutritional educational programs to underserved residents at Rouge Park. - Develop sustainable partnerships with the following local community partners: Oakwood Hospital, Walk Your Heart to Health, National Institute on Minority Health and Health Disparities, the University of Michigan, and Henry Ford Medical Institute - Step 1: Consult with program administrators and stakeholders to gauge current involvement and partners. - Step 2: Determine strategies to increase support from community health partners with CRCAA’s efforts. - Develop community nutritional health educational programming through collaboration with partners. - Step 1: Research through community interview and consultation with partners, the most needed nutritional education strategies. - Step 2: Work with community partners and stakeholders to develop programming for residents that is open to the public and incorporates the Rouge Park as a community resource. - The DOI/VISTA will report progress related to Nutritional Education and Community Health – Healthy Futures quarterly. (Reports completed on the Federal Quarterly schedule and submitted to the VISTA Leader) Objective of the Assignment DOI/VISTA will create opportunities for residents to learn transferable employment skills through service learning opportunities such as the development and maintenance of trails and assisting in the development of educational community health events. For youth participants, the project will encourage future study, employment, and careers in conservation related fields through the development of a Conservation Corps program model - Build programmatic capacity for the development of a conservation corps - Step 1: Consult with RTCA staff and CRCAA to determine eligible community partners in the management of a Conservation Corps - Step 2: Determine fundraising strategies for the development of a conservation corps. - Step 3: Develop community partnerships with local schools in order to gauge interest in a conservation corps amongst students - The DOI/VISTA will report progress related to Economic Opportunity – Employment Quarterly. (Reports completed on the Federal Quarterly schedule and submitted to the VISTA Leader) Objective of the Assignment The DOI/VISTA will develop resources and implement fundraising strategies that will build the capacity of the sponsoring organization to reach underserved communities and build pathways out of poverty. Member Activities: - The DOI/VISTA will develop a 3 year comprehensive fundraising plan that will reflect the needs of the CRCAA and its partners. - Step 1: Working with Supervisor and stakeholders, the VISTA will determine the fundraising needs of the sponsoring organization. - Step 2: The VISTA will research diverse fundraising strategies and opportunities including both private and public grants, sponsorships, and fundraising events for nonprofit partners. - Step 3: The VISTA will produce a best practices report that outlines a fundraising strategy that encompasses 3 full years. - The DOI/VISTA will develop grant proposals to secure future funding to build the sponsoring organizations’ capacity. - Step 1: The VISTA will pursue grant funding that supports programs and projects of the sponsoring organization or nonprofit partner that serve impoverished communities. - Step 2: The VISTA will submit a minimum of four (4) grant proposals during their VISTA term. - The DOI/VISTA will develop Volunteer recruitment and management strategies to increase the number of volunteers working with the program. - Step 1: The VISTA will research and review current volunteer management and recruitment process. - Step 2: The VISTA will determine strategies to expand volunteer involvement in the programs of the sponsoring organization. - Step 3: The VISTA will compile and present a Volunteer management best practices report. - The DOI/VISTA will report on progress related to resource development and fundraising strategies quarterly. (Reports completed on the Federal Quarterly schedule and submitted to the VISTA Leader) Objective of the Assignment The sponsoring organization will support the DOI/VISTA member to broaden his or her professional skillset, creating opportunities for the VISTA to learn and grow in the aspects of their service that correlate with their professional goals. - Overall, the VISTA will commit a minimum of 10% of his or her time to professional development activities such as attending regional conferences, conducting presentations, writing professional papers, building specific skills, and developing professional partnerships.